## To Do and Notes
TO DO | Details | Assigned to | Status
Get email invitation sent out | done | amyd | done
Set up online registration form | done | amyd | done
Visit classes in Superhero guise | Community meeting is Apr 23rd, this might be the best day to visit classes. Should have small brochure to pass out. | amyd
set schedule of events | In process | amyd | done
arrange for food |  | amyd | done
Arrange volunteer shifts | this process appears to take at least 10 hours to ensure load balancing and that parents of wee ones aren't on duty at the same time. | amyd | done
assign rooms | need to get setup spreadsheets and system from Christi | Christi | done
Notify Indianola of meal numbers | Send email to colleen@campindianola.com at least one week prior to our arrival. Need numbers for each meal as well as any dietary restrictions | amyd | done
Send reminder email to guests | packing list, camp rules, what to expect, volunteer shifts, ferry times, | amyd | done
Send reminder to folks bringing stuff | Dessert for Friday; other equipment | amyd
Arrive and set up | Cannot arrive at camp prior to 3pm on Friday.
ACTIVITY PLANNING
Logo Design | Will need 2 people to design and print out potential logos. |  | done
Cape Design | Will need 2-3 people with irons to apply pre-made designs to capes. |  | done
Secret hideout creation | Take a few buddies, build a fort on the beach. Make sure the photographers are looped in! CHANGE: encourage all Beach Supervisors to encourage/guide.
Superhero's vs Sidekicks kickball game | Scheduled for 3-4p. Needs a leader to round folks up and get started. Grownups vs Kids, may need handicap of some type | Saffa, Luke
Mission training (set up an obstacle course) | Ideas: "able to leap tall buildings" - design some boxes to leap over. Kid tunnels to crawl through. 2x4s for balance beams, bricks to support. Tires? String/ropes/bungees between chair legs to step over/between. | davepel, Scott P
Tie Dye | Yvonne has volunteered to lead this with Lisa helping, may as well! | Yvonne B, Lisa J
Slogan or battle cry on the bulletin board | Just need a big piece of butcher paper with some pens
Superhero self defense | Paige will teach an Aikido class. Prefers afternoon, out on the lawn. | Paige W
Beach Cleanup and Mission | Mission: Find the caches of candy? In addition to the usual beach cleanup effort, hide one foil covered container way down at each end of the beach | Susan V
Quick change practice | Change into superhero outfit quickly, in a sleeping bag. Or appliance boxes? |  | canceled
Photo booth: anyone to set up and run? | Cost is around $400. Need one dedicated person to take this and run with it or it won't happen |  | canceled
UPON ARRIVAL AT CAMP
Touch base with camp staff | Anything we need to do right away?
Unload supplies
Set up in Kitchen
Post volunteer assignments
Set up SuperHero Slogan board
Tag the cabins/rooms with family names

## Schedule-basic
FRIDAY, May 16
4:30-9:30p | CHECK-IN: You must sign in!
7-9p | Board games | Totem Lodge
7:30-9:30p | Ping Pong and Foosball | Game room
7:30-10p | Campfire and Music | Fire Pit
9pm | QUIET TIME (lots of people sleep here!) | Totem Lodge
10-10:30p | Back to cabins
11p | LIGHTS OUT
SATURDAY, May 17
8:30a | Breakfast and Camp Staff Welcome | Main Lodge
10a-12p | Morning activities: Build your Superhero Hideout; Rope Swing, Games | Everywhere
10a-12p | Morning Crafts: Superhero masks and capes, Face Paint, Jewelry, Tie Dye | Totem Lodge | Only tie dye needs to be cleaned up. Remind folks to bring shirts! Yvonne needs 2 helpers morning (dye) afternoon (rinse)
10:30a | Snack | Totem Lodge deck | Veggies, hummus, fruit. Leave out until gone.
11a-12p | Superhero Agility Training | Playfield | Obstacle course. Should start setup around 10:45a.
12:30-1:30p | LUNCH | Main Lodge
1:30-2p | Superhero Mission: Beach Cleanup |  | Susan V will lead.
2:30-4:30 | Afternoon Crafts: Superhero masks and capes, Face Paint, Jewelry | Totem Lodge | clean up until 5p
2:30-3:30p | Superhero Self Defense Training | Playfield
3p | Snack
4p | Kickball match: Superheros vs Sidekicks | Playfield
5:30p | Dinner
7-8:30p | ENTERTAINMENT | Totem Lodge deck | Start collecting skit signups in the morning. (Volunteer for this?) Must submit by dinner.
8:30-10:00 | Campfire and Music and S'MORES | Fire Pit
9pm | QUIET TIME (lots of people sleep here!) | Totem Lodge
10-10:30p | Back to cabins
11p | LIGHTS OUT
SUNDAY, May 18
9a | Breakfast | Totem Lodge
10a-11:30a | Cleaning
by 11:30a | Check Out

## Stuff to buy
Item | Count | Details | Date ordered | Amount
Capes | 60 | http://superflykids.com/bulk-capes-set-10-promo | 2014-03-11 | 180
Transfers for cape logos | 50 | ebay | 2014-03-31 | 31
Masks | 96 | Oriental trading | 2014-04-23 | 49.25
Glowsticks | 100 | Oriental trading
Bubbles | 48 | Oriental trading
Additional masks | 24 | Oriental trading (replacement order) | 2014-04-29 | 13
Songbooks | 35 | Update old book | 2014-04-18 | 135.98
Snacks |  | Trader Joes | 2014-05-15
Snacks |  | Costco | 2014-05-15
Snacks |  | Fred Meyer | 2014-05-15
Subtotal: food and supplies purchased by AmyD |  |  |  | 409.23
Jewelry | various | Any pieces needed? At this point, assume NO, prep for next year. |  | 0
Tie dye |  | Yvonne will purchase. |  | 120
First aid supplies? |  | Stephanie purchased. |  | 9.58
Subtotal: Supplies purchased by others |  |  |  | 129.58
Grand total: Supplies and Snacks |  |  |  | 538.81

## Stuff to bring
Items from school | Who's bringing it
Drink coolers, 2 | Davepel
Lego bin | Davepel
Microphones, speaker, stands | Davepel
Jewelry kit | Davepel
First aid kit | Davepel
Songbooks (recycle?) | Davepel
Facepaint, "Other" box | Davepel
Buckets (4) and bubble wands | Davepel
Butcher paper | Davepel | for the slogans on the wall
Markers, permanent | Davepel | for the capes. From Mrs Glassey
Markers, washable | CrisP | for the slogans on the wall. From Mrs Jewell.
Scissors | CrisP | to cut out cape designs. From Mrs Jewell.
Items from families | Who's bringing it
Tablecloth | Davepel | for logo iron on
Clipboards, 2 | Davepel | skit sign up; sign in and out
Soccer Goals | Davepel
Walkie talkies | Davepel
Box of pint glasses | Amyd
Roasting sticks for marshmallows | Amyd
Masking/blue tape | Amyd
Glycerin | Amyd
Baseball bases | Oemig
Iron | Cariann Carlson
Iron | Sunni Bannon
Iron | Leah Meigs
Iron | Maki Imada
Iron | Julie Hoyt
Roasting sticks for marshmallows | Bannon
Roasting sticks for marshmallows | Weinrod
Walkie Talkies | Chee
Items for obstacle course
Tablecloths for tunnels, 2 | Davepel
4x6 posts, 2 | Davepel
Ropes n sticks, 2 set of 10? | Davepel
Cardboard "buildings", 2 | Davepel
Baby dolls, 2 | Davepel
"Start" and "End" box | Davepel
Outdoor activity to share | Baker
Outdoor activity to share | Crabbe
Outdoor activity to share | Kaperick
Outdoor activity to share | Salmon

## Food
| Family | Bringing
Friday night Dessert (need 12) | Carlson
Romano
Pederson
Weinrod
Hoyt
Meigs
James/Quincoses
Imada
Oemig
Bannon
Watson
Oje
Snack and other food | Soy milk, 3 boxes | Trader joes | 3 boxes
| Tea | Trader joes | 300 servings~12 boxes. Check with Jennifer if Hospitality has any.
| Popcorn | Trader joes
| Hummus cups | Costco
| Celery | Costco
| Snap peas | Costco
| Fruit leather | Costco
| String cheese | Costco
| Popcorn bags | Costco
| Marshmallows | FM
| Chocolate | FM
| Graham crackers | FM
| Apples | FM
| Carrots | FM
| plastic serving gloves | FM
| Dawn dish soap | FM | for bubbles
| Milk | on island
| Ice | on island

## Volunteers
Task | Location | Time | Who 1 | Who 2 | Who 3
Friday
Task | Location | Time | Who 1 | Who 2 | Who 3
Check-in table (3) | Potlach porch | 4:30-7p | Amy Drackert | Christi Damico | Cariann Carlson
Late check-in | Totem Lodge | 7-9:30p | Amy Drackert
Medical officer | Totem Lodge | on call, with walkie | Amy Drackert
Game room supervisor | Potlach, lower level | 7:30-8:30p | Carmen Kaperic
|  | 8:30-9:30p | Pam Hurst-Guerra
Board Games | Totem Lodge | 7:30-8:30p | Larissa Peay | Leah Meigs
|  | 8:30-9:30p | Susan Watson | Lindsay Corneilus
Dessert help/cleanup | Totem Lodge | 7:30-8:30p | Rachel Turpin | Brandon Turpin
|  | 8:30-9:30p | John Meigs | Allison Weinrod
Campfire song leader | Fire pit | 7:30-10p | Anton Urban
Campfire attendant |  | 7:30p (Light) - 8:30p | John Kammerer
|  | 8:30-9:30p | Chris Oje
|  | 9:30-fire is out | James Weinrod
Saturday
Task | Location | Time | Who 1 | Who 2 | Who 3
BREAKFAST | Potlach | 8:30a
Check-in table | Potlach Porch | 8:00-9:30a | Amy Drackert
| various; will have radio | Anytime later | Amy Drackert
Medical officer | on call | 8a-12p | Lloyd Chee
Check at Totem lodge, the on-call medical officer will have one of the radios |  | 12p-4p | Stephanie Develle
|  | 4-7p | Susan Vossler
|  | 7-10p | Mark Vossler
Superhero Agility Training | Playfield | 10a-noon | David Pelton | Scott Pederson | Erik Odderson & Adam Romano
Okay, it's an obstacle course…
Kitchen cleanup (morning) | Totem lodge kitchen | 9:30-11a | Julie Hoyt | James Weinrod
Just keep the various glasses and dishes washed (dishwasher) |  | 11a-12:30p | Rob Hoyt | Anton Urban
Rope swing | Rope Swing | 9:30-10a | Amy Drackert | Anton Urban
Make sure to pass the key off to the next adults at the swing. Last one lock it up! |  | 10-10:30 | Casey Peay | Mark Baker
|  | 10:30-11a | Ingrid Salmon | Rick Crabbe
|  | 11-11:30a | Paige Watson | Pete Kaperick
|  | 11:30a-12p | Patrick Bannon | John Meigs
|  | 12-12:30p | James Weinrod | Paul Quincoses
Beach supervision | All along beach | 9:30-10:30a | Patrick Bannon | Eric Oemig | Mark Baker
Encourage the kids to create their secret hideout! |  | 10:30-11:30a | Paul Quincoses | Courtney Romano | Cris Pederson
|  | 11:30a-12:30p | Allison Weinrod | Pam Hurst-Guerra | Ingrid Salmon
Snack, 10:30a (set up,monitor) | Totem Lodge porch | 10a-10:30a | Cris Pederson | Fred Romano
Snack, 10:30a (monitor, clean up) |  | 10:30a-11:15a | Larissa Peay | Shelley Guzik
Face painting | Totem lodge porch | 10a-12p | Katty Aghaseyedali | Tara Crabbe
Cape creation | Totem Lodge main room | 10a-12p | Sunni Bannon | Maki Imada
|  | 10a-12p | Cariann Carlson | Leah Meigs
Mask creation | Totem Lodge main room | 10a-12p | Lindsay Cornelius | Vy Oje
Tie Dye | Totem Lodge porch | 10a-12p | Yvonne Baker leads | Lisa James
|  | 10a-12p | Brynn Baker | Mary Oemig
Jewelry table | Totem Lodge main room | 10a-12p | Susan Watson | Shilpa Reddy
LUNCH | Potlach | 12:30-1:30p
Superhero MISSION: Beach Cleanup |  | 1:30-2:30p | Susan Vossler leads | EVERYONE HELPS!
Kitchen cleanup (afternoon) | Totem lodge kitchen | 2:30-4p | Courtney Romano | Tracy Plank
Just keep the various glasses and dishes washed (dishwasher) |  | 4-5:30p | Fred Romano | David Pelton
Rope swing | Rope Swing | 2:30-3p | David Pelton | Scott Pederson
Make sure to pass the key off to the next adults at the swing. Last one lock it up! |  | 3-3:30p | Aaron Guzik | Erik Odderson
|  | 3:30-4p | Paul Plank | Lloyd Chee
|  | 4-4:30p | James Weinrod | John Kammerer
|  | 4:30-5p | Patrick Bannon | Rick Crabbe
|  | 5-5:30p | Brandon Turpin | Mark Vossler
Beach supervision | All along beach | 2:30-3:30p | Pete Kaperick | Thomas Cornelius | ??
Encourage the kids to create their secret hideout! |  | 3:30-4:30p | John Meigs | Chris Oje | Mark Kruschwitz
|  | 4:30-5:30p | Casey Peay | Aaron Guzik | Paul Plank
Superhero Self Defense Training | Playfield | 2:30-3:30p | Paige Watson leads | Abhishek Mandala | Brady Guzik
Face painting | Totem lodge porch | 2:30-4:30 (clean up) | James Develle | Shelley Guzik
Cape creation | Totem Lodge main room | 2:30-4:30 (clean up) | Julie Hoyt | Stephanie Develle
Mask creation | Totem Lodge main room | 2:30-4:30 (clean up) | Ahmad Hiyeri | Mary Oemig
Jewelry table | Totem Lodge main room | 2:30-4:30 (clean up) | Lisa James | Larissa Peay
Tie Dye (rinsing) | Totem Lodge | 2:30-3:30p | Yvonne Baker leads | Vy Oje | Katty Aghaseyedali
Snack, 3p (setup, monitor) | Totem Lodge porch | 2:30-3p | Tara Crabbe | Susan Watson
Snack, 3p (monitor, clean up) |  | 3-3:45p | Leah Meigs | Maki Imada
Kickball Match! | Playfield | 4p | Thomas Cornelius | Saffa Hiyeri | Luke Pelton
Superheros vs Sidekicks
DINNER | Potlach | 5:30p
Set up for Skit Night |  |  | Sound?? | Sound??
ENTERTAINMENT | Totem Lodge deck | 7-8p | sign-ups: see Tirzah P before dinner
Tirzah is collecting skit signups. Must sign up by dinner! |  |  | [MC?] | [MC?]
Campfire attendant | Fire Pit | 8p (Light) - 9p | Jim Salmon
|  | 9-10p | Rachel Turpin
|  | 10p-fire is out | Lloyd Chee
Campfire song leader | Fire pit | 8:30-10p | Anton Urban?
Campfire S'Mores wranglers | Fire Pit | 9pm | Lindsay Cornelius | Allison Weinrod
Popcorn servers | Totem lodge kitchen | 8:30-9:30p | Cris Pederson | Eric Oemig
Sunday
Task | Location | Time | Who 1 | Who 2 | Who 3
BREAKFAST | Potlach | 9a
Medical Officer |  | 8a-11a | John Kammerer
Cleanup: EVERYONE cleans! | all cabins | Must be done by 11a | EVERONE CLEANS
Cabin inspections | all cabins as folks leave | 10a-11a | Shilpa Reddy | Christi Damico
|  | 11a-11:30a | Susan Watson | Amy Drackert

## Bubbles
Crazy Deluxe Bubbles Recipe
1 cup warm water
2 tablespoons liquid dish or laundry detergent
1 tablespoon glycerin
1 teaspoon white sugar
How to make bubbles: Gently stir all ingredients together and store in a airtight container. These bubbles have staying power! Given the right conditions you might lose sight of your bubbles before they pop!

## Skit Night
Spring Camp Skit Night
Individual or small group acts are limited to 3 minutes.
If the weather is good, it will be outside!
| Who | What
1) | Middles | "Let it Go" from Frozen
2) | DCS Moms
3) | DCS Dads
4)
5)
6)
7)
8)
9)
10)
11)
12)
13)
14)
15)
16)
17)
18)
19)
20)